## Cover sheet
Saltney Ferry C.P School
Post Inspection Action Plan (PIAP)
Chair of Governors: Ann Montagu
Headteacher: Paul Wilcockson
GwE Supporting Improvement Advisers: Vicky Lees and Susan Roberts
Ratified on: 9th January 2023

## Timeline
PIAP Timeline 2023-24
| Spring 2023 |  | Summer 2023 |  | Autumn 2023
| Spring 1 | Spring 2 | Summer 1 | Summer 2 | Autumn 1 | Autumn 2
| Focus - Phonics & Reading | Focus - Writing | Focus- Welsh | Focus- Digital | Focus- Pupil Challenge and attitudes to learning | Focus- Evaluation of progress
Week 1 | Audit of phonic approach - HB | Training for all staff in teaching and planning for language and extended writing-SIA. Develop and agree writing approach-NM | Baseline audit of Welsh language skills in staff and pupils-SM | Audit of Digital resources and skills of staff and pupils-EK&SIA | Audit of pupil attitude to learning through PASS. | Evaluation of progression in Reading and Writing
Week 2 | Phonics Training - HB/SIA. Training for tracking + timetables - NM/SIA | Map out teaching and progression of SPAG across the school- NM | Map out the teaching & progression of skills across the school-SM | Map out teaching & progression of digital skills across the school | Audit of challenge through teaching by focussed lesson observations PW & NM. Develop learning environment. | Evaluation of reading progress through data analysis
Week 3 | Phonic Groups established ensuring level of challenge for all learners tracking of phonics in place. | Training for all staff - effective feedback in writing (AFL)- SIA. Collaborative planning of extended writing cycles - SLT | Training and support provided by Athrawon Bro | Training and support provided by GwE. Effective practice visits to look at learning environments 3-8/planning and assessment | Monitoring of challenge from Governors and SIA- book scrutiny & Learning walks | Evaluation of writing progress through book scrutiny.
Week 4 | SIA support for SLT to monitor application of phonics - SIA | Modelling writing approach for all teachers- Writing masterclass lessons All teachers to observe NM delivering | Modelling effective teaching of Welsh. | Modelling of effective teaching of digital skills across a range of AOLE's | Attitudes to using Welsh across thre curriculum monitored-SM. Training on effective AFL/effective practice visits | Evaluation of progression in Welsh and digital skills
Week 5 | Monitoring of phonics progress- Learning walk - SIA /HB. Identify suitable reading interventions - SIA /CJ. Guided reading training SIA | Monitoring of Guided reading-SLT & Link Governor. Learning walk supported by SIA & SR. | Monitoring of writing progress SLT & Governors. Learning walk and book scrutiny supported by SIAs | Monitoring of Welsh oracy levels across the school-SM, link Governor & Criw Cymraeg | Monitoring of digital skills across the AOLE's | Develop action plan to meet areas of development highlighted through monitoring acticities.
Week 6 | Impact evaluation - SLT (Phonics) Implementation of guided reading approach | Impact evaluation by SLT & Link Governor of guided reading approach Milestone evaluation reading | Impact evaluation - SLT (Writing) & Link Governor capture pupil voice on attitudes to writing - learning walk/book look - supported by SIAs | Impact evaluation - SLT & Link Governor Welsh oracy | Impact evaluation Digital EK & SLT & Link Governor skills | Staff PDR's reflect school improvement priorities and structured timeline completed for next 5 1/2 terms as per the above cycle.
Week 7 |  |  | Milestone evaluation reading & writing | Milestone evaluation reading & writing & Welsh | Milestone evaluation reading & writing & Welsh & Digital | Mapping of actions for each staff member to ensure full coverage of improvement.
Ongoing | R2 Implementation linked to actions listed in R2 tab- Ongoing action to develop and embed Welsh and digital skills | R2 Implementation linked to actions listed in R2 tab- Ongoing action to develop and embed Welsh and digital skills | R2 Implementation linked to actions listed in R2 tab- Ongoing action to develop and embed Welsh and digital skills | R2 Implementation linked to actions listed in R2 tab- Ongoing action to develop and embed Welsh and digital skills | R2 Implementation linked to actions listed in R2 tab- Ongoing action to develop and embed Welsh and digital skills | R2 Implementation linked to actions listed in R2 tab- Ongoing action to develop and embed Welsh and digital skills

## R1
Recommendation 1 - Improve pupils’ reading and writing skills
Lead Person: Nick Martin (writing) supported by Helen Barclay (phonics) and Catherine Jones (ALN) Linked Governor: Jackie Marshall
Current position
Estyn View: Early in the school, most pupils develop a basic knowledge of letters and their associated sounds and use this understanding to help them become readers with a limited degree of fluency. However, as they progress through the school, pupils develop few other strategies to help them read more challenging texts or to establish a thorough understanding of what they are reading. A majority of pupils’ do not write well enough at length, for instance using varied or more complex sentence structures competently. Their grasp of punctuation and spelling is still weak, and the standard of their presentation in many cases is poor. Many pupils in nursery and the youngest class make rapid progress. However, after this beneficial start, pupils’ progress slows too much and is inconsistent. However, as they progress through the school, pupils develop few other strategies to help them read more challenging texts or to establish a thorough understanding of what they are reading.
School View: There is an agreed phonic approach in school, however there is a need for a consistent approach to systematic teaching of phonics, guided reading and writing to ensure progress of learners develops at the expected rate.
Desired Outcomes / Success criteria
Pupils reading and writing skills will improve at the point of data analysis. Pupils can confidently and enthusiastically talk about their reading. Reading Nearly all year 5 & 6 pupils read fluently with a high level of comprehension. Nearly all year 3 & 4 pupils are able to talk about character, plot and theme. Nearly all year 1 & 2 pupils use a range of decoding skills to read fiction and non-fiction texts Nearly all Nursery and Reception pupils acquire sound blends and high frequency words Writing Nearly all pupils across the school will write regularly for a range of purposes. Pupils will use appropriate and interesting vocabulary and a suitable range of punctuation. Pupils will craft and draft their writing from appropriate teacher modelling
Activity | Lead person | Time | Staff development | Cost [time/ finance] | Monitoring | Success Criteria | Evidence
Specific Action to be taken | Who takes responsibility? | By when? | Support needed | Source of funding and how much | Who will check on progress, how and when? | What do we want to achieve? | Links to where the evidence can be found
Audit and analyse phonic approach in school and establish phonic groups for daily delivery. | HB | January 12th 2023 | Release time to complete audit | 2x days supply | Staff meeting 16/02/23 | All learners phonic ability has been assessed and analysis has been used to set phonic groupings. | Notes from phonics groups, Timetables, staff meeting minutes, minutes from Phonics learning walks
Phonic training for Teaching and support staff to ensure effective delivery resulting in a systematic approach | HB & SIA | January 23rd 2023 | SIA support plan for upskilling of delivery of phonics | Staff meeting time for input from SIA/Literacy advisor | PW & NM learning walk 06/02/23 +15/02/23 Governors learning walk 21/03/23 | All staff upskilled to effectively deliver systematic synthetic phonics. Nearly all year 1 & 2 pupils use a range of decoding skills to read fiction and non-fiction texts Nearly all Nursery and Reception pupils acquire sound blends and high frequency words | Staff meetings; learning walks; staff interviews; learner work shows improvement in phonological awareness and application of phonics.
Track phonic progress through 6 weekly re-assessments. | HB & SIA | ongoing | N/A | N/A | PW & NM & CJ 1/2 termly progress meeting. | All learners accessing phonics at appropriate level of challenge ensuring required progress through scheme. Phonological progress highlighted in weekly planning. | Phonics assessment data, weekly planning, termly report on phonological progress, pupil progress meetings.
Monitoring of phonic delivery across whole school. | HB & SIA | Phonics- spring 1 week 6, ongoing | 1/2 day supply every half term on assessment week | use of impact teacher | PW & SIA feedback meeting after assessment week | Delivery of phonics is consistent across the school | Pupil progress data, Tracking documents
Personalised assessments for reading carried out year 2-6. | Teachers | 10th Feb 2023 | N/A | N/A | NM inputs data into tracking document by 17/02/23 |  | Analysis reports; Tracking documents; teacher planning;
Implement guided reading provision based on analysis of learner needs. | NM | February 20th 2023 | Staff training on principles of guided reading by SIA Literacy | N/A | SLT & Link Governor Learning walks 25/03/23 | Nearly all year 5 & 6 pupils read fluently with a high level of comprehension. Nearly all year 3 & 4 pupils are able to talk about character, plot and theme. | Teacher planning; guided reading logs; listening to learners
Implement targetted interventions for reading fluency and comprehension-headsprouts, IFOR and RILL | IFOR- CJ, Headsprouts-HB, RILL-SM/CJ | Feb 10th 2023 | GwE training in Headsprout, iFOR and RILL. | £500 | NM Pupil progress meetings half termly | All learners, where appropriate, accessing targetted intervention for reading fluency | Class timetables; teacher planning; pupil progress data tracking
Monitor and tracking of reading interventions across whole school | CJ | Reading Spring 2 week 5, ongoing | 1/2 day supply every half term on assessment week | N/A | Intervention meetings SLT & CJ half termly | Nearly all learners accessing interventions are making suitable and/or accelerated progress | Progression data of learners
Governors to monitor attitudes to reading across school with focused reading interviews | AM | Spring 2 week 5 | Governors sessions planned in school; members of the governing body are trained teachers so can facilitate this. | Governors Time | Governors/headteacher 21/03/23 | Pupils can confidently and enthusiastically talk about their reading. | Reading interviews, scrutiny of data.
Develop a systematic approach to teaching writing from Year 2-6 | NM | 1st March 2023 | Training provided by SIA on development of language skills through oracy, reading and writing. | 3 days supply use of impact teacher and associated budget | PW, Governors & SIA Monitoring cycle Summer 1 weeks 5&6 | Nearly all pupils across the school will write regularly for a range of purposes. Pupils will use appropriate and interesting vocabulary and a suitable range of punctuation. Pupils will craft and draft their writing from appropriate teacher modelling | Teacher planning
Ensures teachers' planning for writing is collaborative and progressive | NM | Weekly shared PPA time | N/A |  | PW monitors whilst planning. Issues raised in SLT meeting.
Map out teaching of SPAG progressively across the school. | NM | Spring 2 week 2 | Release time to map out skills | 1/2 day supply | PW & CJ Monitor in fortnightly intervention meetings. | Clear strategy of teaching punctuation and grammar skills across the school, leading to enhanced extended writing. | Improvement in punctuation and grammar in books seen in book looks, improvement in quality of extended writing.
Modelling writing approach for all teachers- Writing masterclass lessons All teachers to observe NM delivering | NM | Spring 2 week 4 | NM to model masterclass writing lessons | 1 day supply | SIA to observe and monitor. | A consistent approach to the teaching of writing enables nearly all pupils to craft and draft their writing from appropriate teacher modelling | Teacher planning; book looks; learner voice ; GwE Review points
Training for teachers on use of effective feedback (AFL) to ensure learners can understand next steps to improve their writing. | NM | March 1st 2023 | Training provided by SIA | N/A | SIA monitor May 2023 Summer 1, week 5 | Nearly all learners use effective feedback to improve their writing
Monitoring of learner progression in writing | PW/NM | March 25th 2023 | Support from Link Governor and SIA | N/A Monday SLT time | SLT with Link governor supported by SIA 24/03/23 | Nearly all pupils across the school will write regularly for a range of purposes. Pupils will use appropriate and interesting vocabulary and a suitable range of punctuation. Pupils will craft and draft their writing from appropriate teacher modelling | Book scrutiny report and pupil questionairre responses.
Milestones
Spring |  |  | Summer |  |  | Autumn
Implement systematic phonics approach across the school. Guided reading scheme implemented with consistent approach to planning for writing. Improvement in the robustness of consistent and systematic approaches to these core strategies for planning and teaching. |  |  | Improvement in the application of reading and writing skills by most learners. Accelerated progress in identified groups of learners accessing interventions. |  |  | Embedded systems for planning and delivery of core strategies for reading and writing across the whole school impacting on progress of nearly all learners.
Impact

## R2
Recommendation 2- Improve pupils’ Welsh language and their digital skills
Lead Person: Sarah Morris (Cymraeg) & Esme Kendrick (Digital) Linked Governor: Vicki Lindley & Suzanne Guest & Sue Allmark
Current position
Estyn View Cymraeg: Few pupils make good progress in developing their Welsh language skills. Most pupils respond appropriately to simple classrooms commands. The youngest pupils begin using simple phrases, such as ‘bore da’ confidently and a few thank adults in Welsh independently. Older pupils are beginning to use simple greetings and phrases, for example when responding to the lunch register. As they progress through the school, older pupils communicate simple information about themselves such as saying where they live. However many lack suffcient knowledge and skills and confidence to speak well enough for instance to respond to simple questions in Welsh. There is not a strong enough emphasis on the value of learning to speak the Welsh language.
Estyn View Digital: While they use the internet for research confidently, a minority of pupils do not apply a range of digital skills across all areas of learning well enough. Pupils do not always have a good enough understanding of how to retrieve their own saved work and have a limited understanding of areas of information technology, such as spreadsheets and databases.
School View : The school is working hard to develop a much stronger Welsh culture and identity in order for the Welsh language to flourish. Digital skills are inconsistent across the school so there is a need for the systematic mapping and teaching of digital knowledge.
Desired Outcomes / Success criteria
Pupils Welsh and digital skills will improve at the point of data analysis. Pupils can confidently and enthusiastically use Welsh and digital applications. Welsh Pupils confidently respond to simple commands and greetings in Welsh. Pupils use familiar language patterns confidently. Pupils take part confidently in daily helpwr heddiw sessions. Digital Pupils use digital platforms to enhance their learning in line with the DCF. Pupils can use a range of applications eg. Spreadsheets, databases and communication skills effectively.
There is a clear and systematic approach to the teaching of digital skills and termly planning reflects progression of skills and assesses individual progress. Digital skills build progressively across the school and by Year 6 pupils have the necessary digital knowhow to smoothly transition to the Secondary phase. Cluster lead has established Transition checklist with expectations of skills pupils require in year 7
Activity | Lead person | Time | Staff development | Cost [time/ finance] | Monitoring | Success Criteria | Evidence
Specific Action to be taken | Who takes responsibility? | By when? | Support needed | Source of funding and how much | Who will check on progress, how and when? | What do we want to achieve? | Links to where the evidence can be found
Athrawon bro to support teachers ascertain baseline of Welsh Language oracy skills across the school | SM | Summer 1 week 1 | Athrawon bro to upskill and train staff | £90 x 2 Half day release time Funded through Athrawon Bro | Athrawon bro, SLT &SIA | Staff upskilled to support pupils to confidently and enthusiastically use Welsh language skills | PDR, Welsh drive, book looks, learning walks,Questionnaires
Criw Cymraeg and SM to analyse questionnaire results and draw up targets. | SM a Criw Cymraeg |  | Athrawon bro to support Criw Cymraeg questionnaire | Half day release time funded by Athrawon bro | Welsh meeting every other week on Friday Mornings with SM & SLT | Clear baseline of current provision for Welsh to inform whole school improvement planning | Action plan and non-negotiables in Welsh reccomendation drive
Training and modelling of effective teaching of Welsh oracy skills across the AOLE's | SIA | Summer 1 week 3 & 4 | Athrawon bro to model good practice in each year group. Structured plan of training observed. | N/A | Welsh skills monitored in 6 week cycle summer 2 week 4 SLT, Governors & SIA | Nearly all pupils confidently respond to simple commands and greetings in Welsh. Nearly all pupils use familiar language patterns confidently. Nearly all pupils take part confidently in daily helpwr heddiw sessions. | PDR, Welsh drive, book looks, learning walks.
Establish a Welsh ethos in each classroom with the use of daily tasks, such as Helpwr Heddiw | SM Criw Cymraeg |  | Athrawon bro & SM to support planning and progression within classroom activities | Impact teacher |  | Achieve Cymraeg Campus bronze award. | PDR, Welsh drive, book looks, learning walks.
Map out the teaching & progression of Welsh skills across the school | SM & Athrawon bro | Summer 1 week 2 |  |  |  | Nearly all pupils confidently respond to simple commands and greetings in Welsh. Nearly all pupils use familiar language patterns confidently. Nearly all pupils take part confidently in daily helpwr heddiw sessions. | PDR, Welsh drive, book looks, learning walks.
Monitoring of progress in the use of Welsh oracy | SM Criw cymraeg | Welsh Summer 2 week 5 | Support from Link Governor and SIA | N/A Monday SLT time
Monitoring and evaluation of Welsh through cluster schools collaboration project (School Partnership Programme) | PW & NM & SM | 20th Jan 2023, termly ongoing | Planning time for sharing day. HT and SM 1/2 day planning | Impact teacher | SIA & Criw Cymraeg | Sharing of good practice across the cluster establishes a shared approach to the development of Welsh culture. External audit from other senior leaders enhances the robustness of planning and progress. | Quality assurance report from cluster/partner schools.
Audit IT equipment to ascertain need for new/replacement equipment | Teachers | Summer 2 week 1 | Staff meeting time/1 staff meeting dedicated to audit | 1/2 day supply use of impact teacher. | SLT, EK to look at audit results and order resources needed this finiancial year. | IT audit informs action plans to ensure nearly all pupils use digital platforms to enhance their learning in line with the DCF. Nearly all pupils can use a range of applications eg. Spreadsheets, databases and communication skills effectively. | Digital drive, book looks, learning walks.
Audit IT skills of staff and pupils using google questionnaire in order to set individual and group targets and inform the mapping of skills. | All staff/pupils |  | Designated lesson time Support from Gwe - External verification from colleague in GwE | Lesson designated to auditting skills through google forms. £0 | SLT create baseline from initial audit then monitor progression using tracking documentation.
Systematic approach to teaching explicit digital skills mapped and informing teacher planning | EK/PW | Summer 2 week 2 & 3 | EK 5 days | N/A | Digital skills monitored in 6 week cycle Autumn 1 week 4 SLT, Governors & SIA |  | PDR, Digital drive, book looks, learning walks.
Map Teaching of digital apps across school. | Digital SIA & EK |  | Support from GwE Digital lead to model good practice in each year group. | N/A |  | Pupils use digital platforms to enhance their learning in line with the DCF. Pupils can use a range of applications eg. Spreadsheets, databases and communication skills effectively. | Digital shared drive, learning walks, book looks, digital portfolios.
Training and modelling effective teaching of digital skills across the AOLE's | [6 empty] | Lesson observations, Digital leader learning walks, digital portfolio scrutiny.
Collaborative work with the digital facilitators from the cluster to share good practice and enhance digital provision | EK | Ongoing Cluster dates to be finalised | EK leadership development programme to form project on enhancing digital provision across the cluster | EK 4 x 1/2 day supply from impact teacher budget |  |  | Digital recommendations folder, Cluster workshops external verification from SIA
Monitoring of digital skills across AOLEs | SM & Criw cymraeg | Autumn 1 week 5 | Support from Link Governor and SIA | SLT meeting time |  |  | Lesson observations, Digital leader learning walks, digital portfolio scrutiny.
Milestones
Spring |  |  | Summer |  |  | Autumn
Digital skills are mapped across the school and explicitly referenced in planning. The teaching of digital skills is directly linked to the topic to ensure crosscurricular opportunities. A Clear welsh ethos is beginning to be established with a clear action plan of progress towards cymraeg campus bronze award. |  |  | Digital skills are embedded in weekly and termly planning and AFL strategies used to highlight progress and next steps for individual pupils. Pupils are able to confidently operate a range of apps and systems and can confidently perform IT tasks in line with their expected stage of development. welsh language is used more frequently around the school and there is a clear Welsh ethos established. Pupils are beginning to apply their Welsh language skills to all areas of the curriculum. |  |  | Digital skills permeate all areas of the curriculum to enhance learning whilst teaching the required skills on the digital skill continuum. Staff are confident in the delivery of digitasl skills and have the necessary training to support the pupils. A Welsh ethos is apparent both within and outside the classroom and the school is identifiable as a school in Wales. Pupils are proud to attend a Welsh school and use the welsh language throughout all aspects of the curriculum.
Impact

## R3
Recommendation 3- Ensure that teachers maintain high expectations, and challenge all pupils to achieve consistently
Lead Person: Paul Wilcockson & Catherine Jones Linked Governor: Ann Montagu
Current position
Estyn View: Where the quality of teaching is less effective and pupils are less interested and challenged by their tasks, a minority struggle to maintain focus in group settings even for short periods of time. Pupils are starting to identify the level of challenge that is appropriate to their stage of development. At present this often involves them working through tasks of increasing difficulty rather than selecting the challenge that is most appropriate for them initially. Pupils respond well to opportunities to reflect on whether they have been successful in their learning tasks or not. However, the value of this is often limited by the quality of the success criteria provided by teachers, which do not always help them understand what makes their work effective. [Teachers] do not provide appropriate challenge consistently enough and their expectations of the quality and standard of pupils’ work is not always high enough. As a result, pupils do not make strong enough progress in important areas of their learning. Teachers’ use of coloured highlighters shows pupils where they have been successful and where they can make further improvements. However, there are insufficient opportunities for pupils to act on this helpful guidance. Teachers provide a few opportunities for pupils to assess their own work and that of their peers. However, the criteria that they give to pupils to do this is too often a list of tasks to complete and not always focused well enough on helping pupils to understand what will improve their work Professional learning has not always addressed well a few ongoing priorities nor had a strong enough impact on pupils’ learning, such as whole staff training on raising standards in pupils’ writing. Overall, there has been limited professional learning focusing on improving the quality of teaching.
·
School View: High expectations are seen in some lessons however this is inconsistent. There needs to be an agreed set of 'Non-negotiables' in terms of expectations that are apparent in each lesson. pupils should be challenged in each lesson appropriately and have input into the level of challenge. The use of the zone of proximal development in the Junior department needs to empower pupils to own their learning journey whilst ensuring appropriate challenge
Desired Outcomes / Success Criteria
Teachers will plan and provide appropriately challenging activities. Teachers facilitate pupils learning to show them how to improve and pupils are able to respond. Pupils are actively engaged and focussed on tasks. School leaders consistently monitor challenge and expectations through 6 week improvement cycle activities.
Activity | Lead person | Time | Staff development | Cost [time/ finance] | Monitoring | Success Criteria | Evidence
Specific Action to be taken | Who takes responsibility? | By when? | Support needed | Source of funding and how much | Who will check on progress, how and when? | What do we want to achieve? | Links to where the evidence can be found
Agree timetable and classroom expectations/non-negotiables to be in place for all lessons. Create expectation charter for school. | PW & Teachers | 19th Jan 2023 | SIA support. Time in staff meeting to create charter | Staff meeting time | 6 weekly cycle will be carried out by SLT, Governors & SIA focussing on all recommendations systematically. | All staff adhering to agreed timetable and charter to ensure consistency across the school | Minutes of staff meetings, lesson charter, learning walks with expectation focus, pupils books, learner voice survey
Staff challenge all pupils by having a clear and realistic understanding of pupil attainment in phonics, reading, writing, digital and Welsh | NM & PW | Phonics- spring 1 week 6, Reading Spring 2 week 5, Writing Spring 2 week 5, Welsh Summer 1 week 6, Digital summer 2 week 5 | Staff meeting time to establish what attainment and progress looks like | Staff meeting time | SLT Weekly pupil progress meetings to update tracking document. Monitoring cycle for each area scrutinises level of challenge. Governors and SIA quality assure challenge at review points. | An agreed progress target for each pupil is set within pupil progress meetings to ensure clarity around targets for each learner. | SLT tracking shared drive containing all tracking documents including phonics, reading, maths, progress steps.
Further develop planning processes to ensure all learning experiences provide appropriate levels of challenge | NM & PW | Recurring Thursdays | PPA time shared on Thursday afternoons | Use of impact teacher budget | Planning placed in planning shared drive each Friday PW to digitally sign on Fridays. | Collaborative planning systematically maintains consistently high levels of challenge across all classes. Nearly all pupils are actively engaged and focussed on tasks | Planning shared drive - impact in classroom monitored through learning wallks pupil voice
Visit schools to observe effective practice in 3-8, regarding learning experiences, pedagogy and learning environments | 3-8 staff | Mar 14th 2023 | FL SIA support to identify good practice within schools to visit. | Use of impact teacher to release staff | Staff present findings to governors and discuss implementation plan | Teachers will plan and provide appropriately challenging activities. Nearly all pupils are actively engaging in tasks within purposely focussed learning environments. | Learning walks
Develop learning environment to ensure all learners have access to engaging learning activities | 3-8 staff | Summer 2 week 3 | FL SIA supporting class teachers to develop learning environment |  | FL SIA & NM
Audit of pupil attitudes to learning through PASS to ascertain percieved level of challenge within lessons. | CJ | Autumn 1 week 1 | Support staff to conduct PASS surveys | £1000 | SLT scrutinise data Autmun 1 week 2 | Nearly all pupils are actively engaging in tasks within purposely focussed learning environments.
Training for teachers on effective practice in AFL to improve challenge in all areas of teaching and learning | NM & CJ | Autumn 1 week 4 | SIA to deliver AFL training | Staff meeting time | PW, Link Governor & SIA to observe AFL practice. Autumn 2 week 5 | Teachers using effective AFL strategies which enable learners to respond to feedback and understand next steps in their learning. Teachers will plan and provide appropriately challenging activities within reading, writing, digital and Welsh. | Book looks with AFL focus, learning walks
Visit schools to observe effective practice in AFL, focusing on independent learning, self/peer feedback and success criteria | PW & Teachers |  | SIA support to identify good practice within schools to visit. | Use of impact teacher to release assistant head | Staff present findings to governors and discuss implementation plan
Milestones
Spring |  |  | Summer |  |  | Autumn
After baselining pedagogical strengths and areas for development across the teaching staff there is a clear training plan to upskil areas that are lacking.the school has established an agreed set of expectations that should be present in each lesson. after inset on writing effective success criteria, success criteria observed in each lesson is appropriate and provides the challenge pupils need to develop. |  |  | Planning contains valuable AFL information that informs next steps and there is a systematic approach to the teaching of core Literacy, Numeracy and digital skills. previous planning is available to show progression in skills and informs next steps in learning. Learning walks and book scrutiny reveals high expectations in all lessons and appropriate challenge. |  |  | High expectations are observed in all lessons using the schools agreed set of expectations. Pupils are challenged appropriately in all lessons.
Impact

## R4
Recommendation 4- Implement effective procedures to evaluate the work of the school and address identified areas for improvement robustly
Lead Person: Paul Wilcockson & Nick Martin Linked Governor: Ann Montagu
Current position
Estyn View : At present the school does not evaluate itself nor plan for improvement robustly enough. As a result, it does not always address shortcomings in teaching and in learning effectively. Currently the school does not evaluate the quality of learning and teaching in sufficient detail. As a result, overtime, leaders have not identified well enough some important shortcomings in teaching and learning, such as pupils’ underdeveloped reading skills. Subsequently, leaders have not been able to focus improvement priorities or professional learning on areas that need improvement sharply enough. Over time, leaders have managed the performance of staff suitably. For example, they have developed whole-school targets that link with national priorities helpfully. However, these have had an inconsistent impact on the quality of teaching and learning at the school. Previously, [governors] gathered a comprehensive range of information through visits to the school, such as about how pupils of different ages and stages of development are supported and challenged in the classroom. However, they have not fully restarted this helpful work following periods when they could not access to the school. Therefore, while they question the school helpfully, for example about the impact of the class structures on pupils’ learning, they do not yet have a sufficient range of independent information. Leaders recognise that they are not currently monitoring and evaluating the impact of targeted groups sufficiently well. As a result, they are not clear about how well the additional support they provide improves pupils’ learning
·
School View: Effective procedures of self-evaluation and monitoring of teaching and learning were in place before the pandemic however they need re-establishing and enhancing to ensure that leaders have a thourough understanding of strengths and areas for development.
Desired Outcomes / Success criteria
Effective monitoring has an impact on performance throughout the school. Areas identified through monitoring are addressed robustly through training, coaching, mentoring and performance management. Leaders, including Governors, provide appropriate challenge where teaching and learning is not effective.
Activity | Lead person | Time | Staff development | Cost [time/ finance] | Monitoring | Success Criteria | Evidence
Specific Action to be taken | Who takes responsibility? | By when? | Support needed | Source of funding and how much | Who will check on progress, how and when? | What do we want to achieve? | Links to where the evidence can be found
Timetable for monitoring and self evaluation | SLT | 6 weekly cycle | SIA support with monitoring processes. | N/A | Progress milestones built into cycle with responsibility on PW, Governors & SIA | Structured Timetable of school improvement activities established and implemented to identify areas for development. | Learning walks, book looks, reading sessions, phonics sessions and data
Training in effective tracking processes to ensure impact on learning | NM & CJ | Training 19th Jan 2023. Weekly progress meetings . SIA support ongoing | SIA to train and support use of the GwE tracker. Regular release time on Monday afternoons to scrutinise progress of groups of learners to ensure consistency across school. | Use of impact teacher | PW - weekly pupil progress meetings, ALNCo fortnightly intervention meetings. | Effective tracking ensures pupils are identified and supported. Interventions are tracked and put into place where needed. | Tracker - shared drive; pupil progress data
Coaching in effective monitoring processes for SLT and teaching staff | PW &SIA | Phonics- spring 1 week 6, Reading Spring 2 week 5, Writing Spring 2 week 5, Welsh Summer 1 week 6, Digital summer 2 week 5 | Coaching from SIA to develop effective monitoring processes | N/A | SLT, Link Governor & SIA regular milestone reviews. | Effective monitoring has an impact on performance throughout the school. | Assessment data, weekly planning, termly report progress, pupil progress meetings.
Monitor and tracking of learner progress in reading, Writing, Digital & Welsh | CJ
Governors to scrutinse attitudes to reading across school with focussed reading interviews | AM | Spring 2 week 5 | Governors sessions planned in school; coaching in effective monitoring processes by SIA | N/A | Governors sessions each half term built into monitoring cycle | Leaders, including Governors, provide appropriate challenge where teaching and learning is not effective. | Monitoring feedback in Governors minutes
Governors to monitor improvements across reading, writing, digital and Welsh | AM | Phonics- spring 1 week 6, Reading Spring 2 week 5, Writing Spring 2 week 5, Welsh Summer 1 week 6, Digital summer 2 week 5
Performance management processes link directly to continuous professional development to improve teaching and learning. | PW | Autumn 2 week 6 | Support from SIA to improve processes. | HT Time with SIA | PW 1/2 termly progress meetings with teachers. Teachers hold 1/2 termly progress meetings with support staff. | Areas identified through monitoring are addressed robustly through training, coaching, mentoring and performance management. | PDR paperwork
Termly milestones are set for analysis and evaluation of progress against improvement targets, involving all stakeholders | AM & PW | Last Thursday of each Term | Priority reports |  | Progress milestones built into cycle with responsibility on SLT, Governors & SIA (See timeline for details) | Governors act as critical friend to Headteacher and scruntinise school improvement. Governors are aware of progress towards recommendations. | Milestone evaluation reports
Milestones
Spring |  |  | Summer |  |  | Autumn
Monitoring timetable established. Processes agreed and mapped out across the year. Clear expectations and success criteria are explicitly understood and being followed. |  |  | Processes are established and each member of teaching staff has ownership of the area that they lead on. Regular feedback in staff meetings around progress, is given with each lead accountable for their area. |  |  | Quality of monitoring and scrutiny, including evaluative reports, is robust across the school. School improvement plans contain sharp actions and clear success criteria. Clearly identified roles and responsibilites for all staff. School has effective systems for monitoring and supporting improvement in teaching and learning. Senior leaders take repsonsibility for montoring and evaluating standards of provision.
Impact

## R5
Recommendation 5- Ensure that planned learning experiences build on pupils’ knowledge, skills and understanding systematically
Lead Person: Nick Martin & Esme Kendrick & Helen Barclay Linked Governor: Val Sanders & Kim Shallcross
Current position
Estyn View: [There is] a lack of structure for the progressive and continuous development of pupils’ knowledge and skills over time, for example in pupils’ literacy and digital skills, [meaning] there is little coherence in pupils’ learning journey. They do not provide appropriate challenge consistently enough and their expectations of the quality and standard of pupils’ work is not always high enough. As a result, pupils do not make strong enough progress in important areas of their learning.
School View: Skills are not tracked or planned explicitly enough at the moment, leading to cross over and ambiguity within year groups. A systematic approach to the teaching of skills and the progression of skills will strengthen pupil progress.There are effective planning procedures in the early years that will be adapted and embedded throughout the school.
Desired Outcomes / Success criteria
Teachers will plan systematically from the available frameworks. Pupils knowledge, skills and understanding develop progressively. Teachers focus on knowledge, skills and understanding to ensure appropriate progression for all pupils. All pupils are clear of their success criteria eg. Must, Could & Should. Regular book scrutiny shows progression across all key skills.
Activity | Lead person | Time | Staff development | Cost [time/ finance] | Monitoring | Success Criteria | Evidence
Specific Action to be taken | Who takes responsibility? | By when? | Support needed | Source of funding and how much | Who will check on progress, how and when? | What do we want to achieve? | Links to where the evidence can be found
Audit and review skills progression of phonics, Writing, Welsh & Digital | NM, HB, SM, EK | Spring 1 reading; spring 2 writing; summer 1 Welsh; summer 2 digital | SIA training to ensure staff have a thorough knowledge and understanding of progression | Impact teacher to release. Twilight sessions on tracking approach | NM & SIA progress meetings, feedback in SLT meetings | Teachers will plan systematically from the available frameworks. Pupils knowledge, skills and understanding develop progressively. Teachers focus on knowledge, skills and understanding to ensure appropriate progression for all pupils. | SLT tracking shared drive
Learner progress tracking tool informs planning in all classes to address next steps in reading, writing, Welsh and digital skills for each learner | PW | 19th Jan 2023
Map progression of literacy, numeracy and digital skills across the whole school | SLT | Spring 1 reading; spring 2 writing; summer 1 Welsh; summer 2 digital | SIAs to support use of frameworks to systematically map skills for planning | Impact teacher to release. | SIA and Governors to monitor planning |  | Book looks and teacher planning
Cohesive planning focuses on opportunities for the appropriate level of cross-curricular skills to be applied | SLT | Weekly PPA planning and monitoring | Sharing of effective practice; Staff to collaboratively plan in Infant/Junior teams to ensure skills progression | Impact teacher time | SIA & Governors monitor planning file |  | Planning shared drive - impact in classroom monitored through learning wallks pupil voice
Staff to observe effective practice in another setting, to quality assure standard of planning and assessment processes | SLT | Summer 2 week 3 | PW | Impact teacher and HLTA to provide cover 5 days | PW & Governors | Teachers plan cohesively and systematically from the available frameworks, focusing on skills progression across the school. | Book looks; learning walks; listening to learners;
Teachers identify levels of prior knowledge and skills effectively (AFL) and use them to plan next steps | NM | Autumn 1week 4 | SIA guidance, HT. Release time for staff to attend training with SIA | Impact teacher | SLT monitor autumn 2 | All pupils are clear of their success criteria eg. Must, Could & Should. Regular book scrutiny shows progression across all key skills. Teachers will plan systematically from the available frameworks.
Milestones
Spring |  |  | Summer |  |  | Autumn
All staff consistently using the new planning format and using AFL to inform next steps of planning. |  |  | Whole school planning is embedded, evaluated and refined to meet the needs of every class and all learners. |  |  | Nearly all learners show appropriate levels of progress , with those targetted for intervention showing accelerated progress, in reading, writing, numeracy, digital and Welsh skills.
Impact